## Bug Reports
Demoblaze Bug Reports — 9 Bugs
Bug ID | TC ID | Title | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Screenshot
BUG-001 | TC-014 | Broken image icon shown instead of placeholder when product image fails to load | 1. Open DevTools → Network tab 2. Block any product image URL 3. Refresh the page | A placeholder image appears instead of a broken image icon | A broken image icon is displayed with no fallback | Minor | Low | Open | Screenshot_2026-04-23_101221.png
BUG-002 | TC-020 | Previous button is functional on the first page and changes product listing | 1. Open home page 2. Make sure you are on page 1 3. Click Previous button | Nothing happens or button is disabled | Button works and changes the displayed products | Medium | Medium | Open | Screenshot_2026-04-21_083251.png
BUG-003 | TC-023 | Invalid product URL loads page with 'undefined' data instead of error message | 1. Type invalid URL: demoblaze.com/prod.html?idp_=99999 2. Press Enter | Appropriate error page or 'Product not found' message | Page loads with name, price and description all showing 'undefined' | High | High | Open | Screenshot_2026-04-23_103214.png
BUG-004 | TC-026 | Guest user can add products to cart and cart persists without authentication | 1. Do not login 2. Open any product 3. Click Add to cart 4. Open cart | System prompts user to login or shows an error message | Product is silently added and fully saved in cart with no authentication | High | High | Open | Screenshot_2026-04-23_103758.png Screenshot_2026-04-24_230717.png
BUG-005 | TC-034 | Credit card field accepts alphabetic characters during checkout | 1. Add product to cart 2. Click Place Order 3. Enter letters in credit card field 4. Click Purchase | System rejects letters and shows a validation error | Order is completed successfully with letters in credit card field | High | High | Open | Screenshot_2026-04-24_224427.png
BUG-006 | TC-035 | Credit card field accepts numbers exceeding 16 digits | 1. Add product to cart 2. Click Place Order 3. Enter 38-digit number in credit card 4. Click Purchase | System rejects card numbers that are not exactly 16 digits | Order confirmed successfully with a 38-digit card number | High | High | Open | Screenshot_2026-04-24_225018.png
BUG-007 | TC-036 | Checkout accepts expired card year without validation | 1. Add product to cart 2. Click Place Order 3. Enter past year (e.g. 2020) in Year field 4. Click Purchase | System rejects expired year and shows validation error | Order goes through successfully with expired year | High | High | Open | Screenshot_2026-04-24_225018.png
BUG-008 | TC-037 | Name field accepts numeric-only input during checkout | 1. Add product to cart 2. Click Place Order 3. Enter numbers only in Name field (e.g. 12345) 4. Click Purchase | System rejects numeric-only name and shows validation error | Order completed successfully with numbers as name | Medium | Medium | Open | Screenshot_2026-04-24_225018.png
BUG-009 | TC-042 | Contact form submits successfully with all fields empty | 1. Click Contact in navbar 2. Leave all fields empty 3. Click Send message | Validation error appears and message is not sent | Alert shows 'Thanks for the message!!' with no data entered | Medium | Medium | Open | Screenshot_2026-04-24_230418.png